Minutes

Wherryman’s Way Access Improvement project

Stakeholder Meeting

Meeting Date: Thursday 22nd June 2023

Start: 10:00	   Finish:  11:30

Venue: Microsoft Teams

Invitees / Attendees:

| Name | Organisation | Role | In Attendance? (Y) |
| --- | --- | --- | --- |
| Matthew Hayward (MH) | Norfolk County Council | Lead Projects Manager |  |
| Andrew Middleton (AM) | Norfolk County Council | Team Leader - Greenways Infrastructure | Y |
| James Fisher (JF) | Norfolk County Council | Principal Ecologist |  |
| Samuel Demmen-Sewell (SDS) | Norfolk County Council | Ecologist | Y |
| Martin Caplin (MC) | Norfolk County Council | Trails / Access Officer | Y |
| Lisa Marrison (LM) | Norfolk County Council | Assistant Project Officer - Greenways (Projects) | Y |
| Michael O'Neill (MO) | Norfolk County Council | Assistant Project Officer - Greenways Infrastructure | Y |
| Frances Salway (FS) | Norfolk County Council | Countryside Access Officer |  |
| Katy Owen (KO) | Norfolk County Council | Protected Landscapes Manager |  |
| Dr Dan Hoare (DH) | Broads Authority | Head of Construction, Maintenance and Ecology |  |
| Andrew Walters (AW) | Broads Authority | Waterways and Recreation Officer | Y |
| Helen Sibley (HS) | South Norfolk and Broadland District Council | Green Infrastructure Officer |  |
| Danny Cattermole (DC) | Topbond Plc | Structures Manager | Y |
| Keith Bacon (KB) | Broads Local Access Forum | Chairman |  |
| Martin Sullivan (MS) | Norfolk Local Access Forum |  |  |
| Vic Thomson (VT) | South Norfolk District Council |  | Y |
| Keith Wheeldon (KW) | Bramerton Parish council |  |  |
| Richard Simmonds (RS) | Bramerton Parish council |  |  |
| Richard Atkins (RA) | Surlingham Parish Council |  |  |
| David Johnson (DJ) | Wherryman’s Way Working Group |  |  |
| Emily Leonard (EL) | Broads Authority |  |  |
| Yvonne Wonnacott (YW) | Bramerton Parish Council |  |  |
| Surlingham Parish Council | Surlingham Parish Council |  |  |
| Hayley Goldson (HG) | Chedgrave Parish Council |  |  |
| Deb Downer (DD) | Chedgrave Parish Council |  | Y |
| Simon Downer (SD) | Chedgrave Parish Council |  | Y |
| Parish Clerk | Rockland St. Mary with Hellington Parish Council |  |  |
| Kate Bevington (KB) | Rockland St. Mary with Hellington Parish Council |  |  |
| Joanne Norris (JN) | Rockland St. Mary with Hellington Parish Council |  | Y |

| Item No. | Item | Officer Initials |
| --- | --- | --- |
| 1 | Welcome & apologies AM welcomes the group to the meeting and announces the apologies received from individuals unable to attend. |  |
| 2 | CIL Funding Update AM Presents the slides to the group GNGB funding application unsuccessful – Minutes of the funding review will be forwarded to the group by MO when they become available NCC are currently scoping up options for proceeding with the £216,000 currently available from the previous funding application. MH to investigate the feasibility of further GNGB funding applications NCC are actively looking for alternative funding to support the project. | MO MH |
| 2.1 | Hardley Flood Update AM Presents the first slide to the group. The slide shows an overview map of Hardley Flood with the 4 bridges labelled. The location of the bird hide is also depicted on the map which is between bridge 2 and 3. AM reminds the group of the current path condition and the condition of the 4 bridges. |  |
| 2.2 | Ecology AM hands over to SDS to present to the group. The slides show the 3 protected species present at Hardley Flood, details are shown for the legislation that protects these animals and the endangered species lists they are on. A list of survey discoveries are shown detailing the signs found showing the activity at Hardley Flood for each species. 3 major ecological considerations (European protected species) - Otters on footpath line (possibly raising young). Commissioned consultant for specialist advice - Water voles present. Commissioned consultant for specialist advice - Desmoulin’s Whorl Snails – very specialist species – awaiting new survey results and report Due to the unique case where the Public Right of Way needs to be re-established but there are major ecological constraints which conflict with public access, NCC have met with NP Law for advice on statutory duties and legislation for priority for Public Rights of Way or Ecology. Talking to Natural England regarding next steps Questions (discussion): DD: How long do reports take? SDS Will start first week of July – timescales varied. DD: When do you engage with Natural England? SDS: We apply to Natural England for a licence to disturb or move protected species. It’s a narrow path and adjacent to protected site – unique timeline. AM: Can’t access by land so that has provided challenges. Jan – June has been ecological surveys – it’s a unique situation. DD: What if NE say no? Will we reroute pathways? AM: We don’t want to extinguish PRoW and there is a diversion (however part on road) SDS: It’s rare that Natural England say no, but it’s a unique situation so have to work through it and get mitigation measures in place. AM: Once PRoW is established it will be maintained as a grass (mown) path. |  |
| 2.3 | Revised Timeline AM Presents the slides to the group Broads Authority can submit full planning application which will allow for a 3 year period for delivery. Have to consider best time for ecology and when the River Chet is less busy. Using Broads Authority boats – due to updated schedule, this is likely to be April 2024 now (NCC will look for any opportunity to bring this forward). Cannot start procurement until NCC have received consents. Dredging team have had to commit to a year of works therefore are unavailable until April 2024. The delay to works is estimated at 3 months. NCC will aim to reinstate Hardley flood up to the Bird Hide |  |
| 2.4 | Next Steps Await finalised ecology reports (due end of July) so all data and findings can be provided to Natural England for advice on how to proceed. Confirm what can be delivered with the current budget in Hardley and Bramerton NCC to consider option B of works up to the Bird Hide from the West end of Hardley Flood. Work with Natural England for mitigation and legal advice for planning application. Prepare consents and paperwork for Broads Authority Planning Permission Application Continue to actively search for alternative funding while engaging with GNGB to investigate reapplication feasibility (Summer 2023) Coordinate Broads Authority boats for use in construction in line with new revised timeline. |  |
| 3 | Bramerton FP5 Update AM hands over to AW to present to the group AW reminds group of the condition of the Bramerton section of the project AW shows image of ‘low tide’ and explains that at ‘high tide’, the section of footpath photographed is entirely under water. |  |
| 3.1 | Bank Works Past attempts to restore the back via ‘natural methods’ have failed. Contracted engineers are currently producing the final design for the bank works. Sediment that will be used in construction will be dredged from the river. Sediment in the river has been tested for mercury levels and has been confirmed as being within regulated limits and is safe to use. The design of the new bank will be Gabion Boxes with Rock Rolls behind. This will then be back filled with the dredged material. The reason for Gabion Boxes and Rock Rolls is that it will minimise ‘Wash Out’ from the tidal river, requires less back fill with dredged sediment and allows roots to bed themselves in easier in order to sure up the bank. Willow trees to be coppiced to minimise chance of toppling and pulling up the bank as it falls. Ecology: There are no protected species on site in Bramerton. |  |
| 3.2 | Planning Application Broads Authority Planning permission will be required. A Flood Risk Application Permit (FRAP) will be required. NCC will submit the planning application to Broads Authority. |  |
| 3.3 | Timeline Works expected to be completed Winter 2023 / Spring 2024 Depending on contractor and dredging fleet availability. Question: AM: Will we need to seed where the Gabion boxes will be? AW: We will seek ecology advice prior to making decision. | AW |
| 3.4 | Next Steps Topographical survey to be carried out and bank restoration design to be drawn up by design engineers. Based on these designs, Planning Permission and Flood Risk Application Permit to be applied for. |  |
| 4 | AOB Jubilee Trails The Jubilee Trails have now been Installed and are live The Elizabeth Way – Heacham to King’s Lynn The West Acre Way – Gayton to West Acre The Wendling Way – Dereham to Gressenhall The Chet River Circular – Loddon/Chedgrave The Eastern Maritime Way – Great Yarmouth to Lowestoft DD & SD: signage pointing in the wrong direction – pointing to a dead-end by the mill on the Loddon side pointed to private boatyard. AM will get the route audited – ask MO to action. MO to send out Link to Jubilee Trails Website Reedham Ferry Artwork installed last week (funded through Interreg Experience) Salhouse Discovery Hub – Telescope Pier Broads Discovery Hub at Salhouse Broad , supported with funding from the European Union funded EXPERIENCE project to promote off season experiential tourism and sustainable economic growth. Discovery Hubs are designed to promote The Broads as a sustainable, car free destination, creating a network that provides a way to explore the Broads on foot, by bike and on the water. As accessible information points, they explain the history, wildlife and landscape of the area and will encourage people to visit the many and varied aspects of the National Park. They are great places to relax and soak up the unique atmosphere of the Broads and to access local services, attractions and experiences. LCWIP Public consultation – closes soon – link was sent TO? via email after the stakeholder meeting on 22nd June. Questions: VT: Surlingham stretch has scalloping too, can we have an update? AM: Same landowner but 30ms of lost bank. We will get costs from Bramerton and can cost Surlingham. CIL funding isn’t for legal processes and Surlingham may require dedication of a new PRoW from a permissive path. VT: The original path is so far from the bank now; no reason why permissive path shouldn’t be PRoW. AM: NCC cannot carry out works on a permissive path. VT: Current condition leads to flooding just above the ferry by the canoe storage, so that’s an issue as well as protecting the footpath. AM: NCC & BA will have to work with landowner to find the best solution. Will consider within phase 2 of the project. JN: Rockland broad to Beacham arms is impassable can it be cut? MC: Done 3 times a year – should be cut within next few weeks DD: Raises vegetation cutting issue MC: It is due too, cut according to the schedule – should be in next couple of weeks SDS: There has been a sudden growth with heat and water. DD: Langley dyke to Beacham Arms footpath no longer accessible where Langley abbey is. MC: There is no PRoW going north – if there is it is unregistered – Can look at claiming it but it might have been permissive (Landowner gave permission for public use) and therefore can’t be claimed as Public Right of Way. DD: Who is responsible for Bird Hide? AW: Original plan to repair but was due to come from lottery funding. Ownership still being investigated. BA had budget from Watermills and Marshes HLF project but because this CIL project extended it no longer works with deadline to spend the funding. DD: Can we fix the bird hide now? SDS: Water Voles and Otter activity needs verification and there are construction challenges regarding transport across Hardley Flood. Still need the appropriate consents before carrying out any works. AM: After GNGB meeting, we may be able to add bird hide into re-application in July. DD: Can we consider an alternative route to current diversion? MC: do you know the landowner at Derry Farm? We would need permission. AM: We can investigate feasibility for permissive route MC: End of FP5 is obstructed on the common DD: Can we have checkpoint updates? AM: NCC will send an email update on developments prior to next Stakeholder meeting where necessary Will share today’s slides with the Minutes GNGB will be provided to the group when available MO Sent out LCWIP consultation link via email after the meeting. Local Cycling and Walking Infrastructure Plans - Norfolk County Council | AM MO AM AM AM MO AM MO |
| 5 | Next Stakeholder Update: Thursday 28th September 2023 10:00 – 11:30 |  |